## project_timelines
wp | activity | start_date | end_date
1. Scoping review (Rodent trapping) | 1.1. Study protocol | 2020-12-01 | 2021-02-04
1. Scoping review (Rodent trapping) | 1.2. Search completion | 2021-02-01 | 2021-03-01
1. Scoping review (Rodent trapping) | 1.3. Data extraction | 2021-03-01 | 2021-05-01
1. Scoping review (Rodent trapping) | 1.4. Double checking | 2021-05-01 | 2021-07-01
1. Scoping review (Rodent trapping) | 1.5. Analysis | 2021-05-01 | 2021-07-01
1. Scoping review (Rodent trapping) | 1.6. Draft manuscript | 2021-05-01 | 2021-07-01
1. Scoping review (Rodent trapping) | 1.7. Revise manuscript | 2021-07-01 | 2022-04-01
1. Scoping review (Rodent trapping) | 1.8. Submit manuscript | 2022-04-01 | 2022-04-01
2.0. Rodent trapping | 2.0.1. Study protocol | 2020-09-01 | 2021-01-01
2.0. Rodent trapping | 2.0.2. Pilot visit - SL | 2020-11-12 | 2020-12-12
2.0. Rodent trapping | 2.0.3. Pilot data analysis and report | 2020-12-01 | 2021-02-01
2.0. Rodent trapping | 2.0.4. Revise protocol | 2021-01-01 | 2021-03-01
2.0. Rodent trapping | 2.0.6. Study visit | 2021-04-01 | 2021-05-01
2.0. Rodent trapping | 2.0.5. Additional site setup - SL | 2021-06-12 | 2021-07-15
2.0. Rodent trapping | 2.0.6. Study visit | 2021-07-01 | 2021-08-01
2.0. Rodent trapping | 2.0.6. Study visit | 2021-10-01 | 2021-11-01
2.0. Rodent trapping | 2.0.6. Study visit | 2022-01-01 | 2022-02-01
2.0. Rodent trapping | 2.0.6. Study visit | 2022-04-01 | 2022-05-01
2.0. Rodent trapping | 2.0.6. Study visit | 2022-07-01 | 2022-08-01
2.0. Rodent trapping | 2.0.6. Study visit | 2022-10-01 | 2022-11-01
2.0. Rodent trapping | 2.0.6. Study visit | 2023-01-01 | 2023-02-01
2.0. Rodent trapping | 2.0.6. Study visit | 2023-04-01 | 2023-05-01
2.0. Rodent trapping | 2.0.7. Rodent sample analysis (lab) | 2022-04-01 | 2023-06-01
2.1. Rodent trapping (Population dynamics and distribution) | 2.1.1. Study protocol | 2021-05-01 | 2021-12-01
2.1. Rodent trapping (Population dynamics and distribution) | 2.1.2. Lab work - SL | 2021-06-12 | 2021-07-15
2.1. Rodent trapping (Population dynamics and distribution) | 2.1.2. Lab work - SL | 2022-04-14 | 2022-04-28
2.1. Rodent trapping (Population dynamics and distribution) | 2.1.3. Pilot protocol | 2022-03-18 | 2022-04-02
2.1. Rodent trapping (Population dynamics and distribution) | 2.1.4. Analysis plan (speciation) | 2022-02-01 | 2022-04-01
2.1. Rodent trapping (Population dynamics and distribution) | 2.1.5. Draft manuscript (interim analysis) | 2022-05-01 | 2022-09-01
2.1. Rodent trapping (Population dynamics and distribution) | 2.1.6. Final analysis | 2023-06-01 | 2023-07-01
2.1. Rodent trapping (Population dynamics and distribution) | 2.1.7. Final manuscript | 2023-06-01 | 2023-08-01
2.1. Rodent trapping (Population dynamics and distribution) | 2.1.8. Submit manuscript | 2023-08-01 | 2023-09-01
2.2. Rodent trapping (Lassa serology) | 2.2.1. Study protocol | 2021-09-01 | 2021-12-01
2.2. Rodent trapping (Lassa serology) | 2.2.2. Pilot protocol | 2022-03-18 | 2022-04-02
2.2. Rodent trapping (Lassa serology) | 2.2.3. Lab work - SL | 2022-04-14 | 2022-04-28
2.2. Rodent trapping (Lassa serology) | 2.2.4. Analysis plan | 2022-02-01 | 2022-04-01
2.2. Rodent trapping (Lassa serology) | 2.2.5. Draft manuscript (interim analysis) | 2022-08-01 | 2022-12-01
2.2. Rodent trapping (Lassa serology) | 2.2.6. Final analysis | 2023-06-01 | 2023-07-01
2.2. Rodent trapping (Lassa serology) | 2.2.7. Final manuscript | 2023-06-01 | 2023-08-01
2.2. Rodent trapping (Lassa serology) | 2.2.8. Submit manuscript | 2023-08-01 | 2023-09-01
3. Peridomestic species (Lassa serology) | 3.1. Study protocol | 2021-06-01 | 2021-08-01
3. Peridomestic species (Lassa serology) | 3.2. Pilot protocol | 2021-08-01 | 2021-09-01
3. Peridomestic species (Lassa serology) | 3.3. Sample collection | 2021-08-01 | 2022-01-01
3. Peridomestic species (Lassa serology) | 3.4. Peridomestic species sample analysis | 2021-11-01 | 2022-02-01
3. Peridomestic species (Lassa serology) | 3.5. Analysis plan | 2022-02-01 | 2022-03-01
4. LIPS development | 4.1. Bioinformatics (epitope discovery) | 2020-09-01 | 2020-10-01
4. LIPS development | 4.2. Literature review (assays) | 2020-09-01 | 2020-10-01
4. LIPS development | 4.3. Plasmid production | 2021-05-01 | 2021-09-01
4. LIPS development | 4.4. Assay development | 2021-08-01 | 2021-11-01
4. LIPS development | 4.5. Assay validation | 2022-06-01 | 2022-10-01
4. LIPS development | 4.6. Benchmarking against ELISA | 2022-08-01 | 2022-10-01
4. LIPS development | 4.7. Deployment in SL | 2022-08-01 | 2022-10-01
4. LIPS development | 4.8. Sample analysis | 2022-10-01 | 2023-06-01
4. LIPS development | 4.9. Draft manuscript | 2022-10-01 | 2022-11-01
4. LIPS development | 4.10. Final manuscript | 2022-12-01 | 2023-02-01
4. LIPS development | 4.11. Submit manuscript | 2022-05-01 | 2023-06-01
5. Socio-ecological model of LF | 5.1. Conceptual model | 2020-09-01 | 2022-05-01
5. Socio-ecological model of LF | 5.2. Data acquisition and pre-processing | 2020-11-01 | 2022-06-01
5. Socio-ecological model of LF | 5.3. Model testing and refinement | 2022-02-01 | 2022-08-01
5. Socio-ecological model of LF | 5.4. Model parameterisation | 2022-05-01 | 2022-10-01
5. Socio-ecological model of LF | 5.5. Model application | 2022-10-01 | 2023-02-01
5. Socio-ecological model of LF | 5.6. Draft manuscript | 2023-02-01 | 2023-04-01
5. Socio-ecological model of LF | 5.7. Final manuscript | 2023-04-01 | 2023-06-01
5. Socio-ecological model of LF | 5.8. Submit manuscript | 2023-06-01 | 2023-08-01
PhD timeline | 6.1. Funding | 2020-09-01 | 2023-08-31
PhD timeline | 6.2. Upgrade appraisal | 2021-09-01 | 2021-10-01
PhD timeline | 6.3. PIPS | 2021-11-01 | 2022-02-01
PhD timeline | 6.4. PhD write up | 2023-01-01 | 2023-09-01

## project_spots
activity | spot_type | spot_date
6.4. PhD write up | S | 2023-09-01
1.1. Study protocol | C | 2021-02-04
1.2. Search completion | C | 2021-03-01
1.3. Data extraction | C | 2021-05-01
1.4. Double checking | C | 2021-07-01
1.5. Analysis | C | 2021-07-01
1.6. Draft manuscript | C | 2021-07-01
1.8. Submit manuscript | O | 2022-04-01
2.0.1. Study protocol | C | 2021-01-01
2.0.2. Pilot visit - SL | C | 2020-12-12
2.0.3. Pilot data analysis and report | C | 2021-02-01
2.0.4. Revise protocol | C | 2021-03-01
2.0.6. Study visit | C | 2021-05-01
2.0.6. Study visit | C | 2021-08-01
2.0.6. Study visit | C | 2021-11-01
2.0.6. Study visit | C | 2022-02-01
2.0.5. Additional site setup - SL | C | 2021-07-15
2.1.2. Lab work - SL | F | 2021-07-15
2.1.8. Submit manuscript | O | 2023-09-01
2.1.1. Study protocol | C | 2021-08-01
2.2.8. Submit manuscript | O | 2023-09-01
3.1. Study protocol | C | 2021-07-01
4.1. Bioinformatics (epitope discovery) | C | 2020-10-01
4.2. Literature review (assays) | C | 2020-10-01
4.11. Submit manuscript | O | 2022-09-01
5.8. Submit manuscript | O | 2023-08-01
6.2. Upgrade appraisal | C | 2021-10-01
6.3. PIPS | C | 2022-02-01
3.2. Pilot protocol | C | 2021-09-01
3.3. Sample collection | C | 2022-01-01
4.3. Plasmid production | C | 2021-09-01