## project_timelines
wp | activity | start_date | end_date
1. Rodent trapping | Rodent trapping - field work | 2020-10-01 | 2022-10-01
1. Rodent trapping | Rodent assemblages - pilot analysis | 2021-02-01 | 2021-04-01
1. Rodent trapping | Rodent assemblages - analysis | 2022-06-01 | 2022-11-01
1. Rodent trapping | Rodent assemblages - write up | 2022-08-01 | 2022-12-01
1. Rodent trapping | Prevalence of LASV - pilot analysis | 2021-02-01 | 2021-04-01
1. Rodent trapping | Prevalence of LASV - analysis | 2022-06-01 | 2022-11-01
1. Rodent trapping | Prevalence of LASV - write up | 2022-08-01 | 2022-12-01
2. Prevalence of LASV in humans and non-rodents | Human epidemiology - field work | 2020-10-01 | 2021-10-01
2. Prevalence of LASV in humans and non-rodents | Veterinary epidemiology - field work | 2020-10-01 | 2022-10-01
2. Prevalence of LASV in humans and non-rodents | LIPS development - lab work | 2020-09-01 | 2021-10-01
2. Prevalence of LASV in humans and non-rodents | LIPS validation - lab work | 2021-06-01 | 2023-02-01
2. Prevalence of LASV in humans and non-rodents | LIPS validation - write up | 2022-10-01 | 2023-04-01
3. Modelling | Transmission model - development | 2021-06-01 | 2023-03-01
3. Modelling | Transmission model - write up | 2023-02-01 | 2023-04-01
4. Further/complementary projects | Diagnostics systematic review - analysis | 2020-09-01 | 2020-12-01
4. Further/complementary projects | Diagnostics systematic review - write up | 2020-11-01 | 2021-02-01
4. Further/complementary projects | Qualitative work - field work | 2020-10-01 | 2021-03-01
4. Further/complementary projects | Qualitative work - write up | 2021-02-01 | 2021-06-01
4. Further/complementary projects | Phylodynamics - analysis | 2022-09-01 | 2023-02-01
4. Further/complementary projects | Phylodynamics - write up | 2022-12-01 | 2023-04-01
5. Extension projects | Modelling cases from CFR - analysis | 2020-11-01 | 2021-03-01
5. Extension projects | Modelling cases from CFR - write up | 2020-12-01 | 2021-04-01
5. Extension projects | Risk of LASV export - analysis | 2020-12-01 | 2021-02-01
5. Extension projects | Risk of LASV export - write up | 2020-12-01 | 2021-04-01
6. Professional/skills development | HEA - write up | 2020-09-01 | 2020-11-01
PhD timeline | Funding | 2020-09-01 | 2023-08-31
PhD timeline | Upgrade submission | 2021-04-01 | 2021-06-01
PhD timeline | PhD write up | 2023-01-01 | 2023-08-01

## project_spots
activity | spot_type | spot_date
Rodent assemblages - write up | O | 2022-12-01
Prevalence of LASV - write up | O | 2022-12-01
Transmission model - write up | O | 2023-04-01
Diagnostics systematic review - write up | O | 2021-02-01
LIPS validation - write up | O | 2023-04-01
Qualitative work - write up | O | 2021-06-01
Phylodynamics - write up | O | 2023-04-01
Modelling cases from CFR - write up | O | 2021-04-01
Risk of LASV export - write up | O | 2021-04-01
HEA - write up | O | 2020-11-01
Upgrade submission | U | 2021-06-01
PhD write up | S | 2023-09-01